International School Capstone Project 1 CMU-SE 450_C1SE.57 Project Plan Version 1.1 Date : August 31, 2026 Smart Scheduling - Website for Automated Staff Scheduling and Shift Submitted by Tuan, Le Ha Duc Hien, Le Tran Thanh Nghia, Le Dinh Quan, Huynh Van Minh Luc, Huynh Vu Approved by PhD. Vu, Truong Tien Proposal Review Panel Representative: Name Signature Date Capstone Project 1 - Mentor: Name PhD. Vu, Truong Tien Signature Date

PROJECT INFORMATION

| Project acronym | Smart Scheduling |  |  |  |
| --- | --- | --- | --- | --- |
| Project Title | Smart Scheduling - Website for Automated Staff Scheduling and Shift |  |  |  |
| Start Date | August 26, 2026 | End Date | December 06, 2026 |  |
| Lead Institution | International School, Duy Tan University |  |  |  |
| Project Mentor | PhD Vu, Truong Tien Email: vudalat@yahoo.com Tel: 0914083188 |  |  |  |
| Scrum master / Project Leader & contact details | Tuan, Le Ha Duc Email: lehaductuan05@gmail.com Tel: 0852830905 |  |  |  |
| Partner Organization | Duy Tan University |  |  |  |
| Project Web URL |  |  |  |  |
| Team members | Name | Email |  | Tel |
| 29212761036 | Tuan, Le Ha Duc | lehaductuan05@gmail.com |  | 0852830905 |
| 29201124759 | Hien, Le Tran Thanh | lethanhhien414@gmail.com |  | 0328675911 |
| 29211163309 | Quan, Huynh Van Minh | minhquan251205@gmail.com |  | 0976461574 |
| 29219029552 | Luc, Huynh Vu | huynhvuluc123@gmail.com |  | 0397636350 |
| 29211156998 | Nghia, Le Dinh | dinhnghia1475@gmail.com |  | 0369485344 |

PROJECT PLAN DOCUMENT

| Document Title | Project Plan Document |  |  |
| --- | --- | --- | --- |
| Author(s) | Team C1SE.57 |  |  |
| Date | 31/08/2026 | File name: | C1SE.57_PROJECT_PLAN_Smart_Scheduling_v1.1.docx |
| URL |  |  |  |
| Access | Project and CMU Program |  |  |

SIGNATURE

Document Approvals: The following signatures are required for approval of this document.

| PhD Vu, Truong Tien Mentor | Signature | Date |
| --- | --- | --- |
| Tuan, Le Ha Duc Student ID: 29212761036 Scrum Master | Signature | Date |
| Hien, Le Tran Thanh Student ID: 29201124759 Product Owner | Signature | Date |
| Quan, Huynh Van Minh Student ID: 29211163309 Team Member | Signature | Date |
| Luc, Huynh Vu Student ID: 29219029552 Team Member | Signature | Date |
| Nghia, Le Dinh Student ID: 29211156998 Team Member | Signature | Date |

REVISION HISTORY

| Version | Person(s) | Date | Description |
| --- | --- | --- | --- |
| 1.0 | All members | 30/08/2026 | Create initial Project Plan document. |
| 1.1 | All members | 31/08/2026 | Align scope with single-store Web/Mobile solution, Laravel core, OR-Tools Scheduling Service, GPS attendance, timesheets, optional AI Assistant, and updated Sprint plan. |

TABLE OF CONTENTS

1. PROJECT OVERVIEW	6

1.1 PROJECT DESCRIPTION	6

1.2 SCOPE AND PURPOSE	6

1.3. ASSUMPTIONS AND CONSTRAINT	6

1.4. PROJECT OBJECT	7

1.4.1. STANDARD OBJECTIVES	7

1.4.2. SPECIFIC OBJECTIVES	8

1.5. CRITICAL DEPENDENCIES	8

1.6. PROJECT RISK	8

2. PROJECT DEVELOPMENT APPROACH	9

2.1. TECHNICAL PROCESS	9

2.1.1. REASON FOR SELECTING	9

2..1.2 AGILE METHODOLOGY	9

2.1.3. SCRUM PROCESS	9

2.2. REQUIREMENT CHANGE MANAGEMENT	10

2.2.1 STRATEGY FOR MEETING QUALITY OBJECTIVES	10

2.2.2 QUALITY CONTROL	11

2.2.3 MEASUREMENT PROGRAM	12

2.3 UNIT TESTING STRATEGY	12

2.4. INTEGRATION TESTING STRATEGY	14

2.5. SYSTEM TESTING STRATEGY	14

3. ESTIMATION	14

3.1. SIZE	14

3.2. EFFORT	14

3.3. SCHEDULE	15

3.3.1 PROJECT MILESTONES & DELIVERABLES	15

3.3.2. WORK BREAKDOWN STRUCTURE	17

3.3.3 DETAILED SCHEDULE	17

3.3.4. PROJECT SCHEDULE	28

3.4. RESOURCE	28

3.5. INFRASTRUCTURE	28

3.6. TRAINING PLAN	29

4. PROJECT ORGANIZATION	30

4.1. PROJECT TEAM	30

5. COMMUNICATION & REPORTING	31

6. CONFIGURATION MANAGEMENT	33

7. SECURITY ASPECTS	33

Table

Table 1: Project Description ........................................................................................5

Table 2: Assumptions and Constraints .......................................................................8

Table 3: Standard Objectives ......................................................................................9

Table 4: Project Risk ..................................................................................................10

Table 5: Strategy for meeting quality objectives .....................................................12

Table 6: Quality Control ............................................................................................13

Table 7: Measurement program ................................................................................13

Table 8: Effort .............................................................................................................16

Table 9: Project Milestone & Deliverables ………………………………………...17

Table 10: Detail schedule............................................................................................29

Table 11: Infrastructure.............................................................................................30

Table 12: Training plan..............................................................................................30

Table 13: Project team ...............................................................................................32

Table 14: Communication & Reporting …………………………………………...33

Figure

Figure1: Scrum master...............................................................................................11

Figure 2: Work breakdown structure.......................................................................18

1. PROJECT OVERVIEW

1.1 PROJECT DESCRIPTION

| Project code | Smart Scheduling | Contract type | Internal Project |
| --- | --- | --- | --- |
| Customer | Duy Tan University | End-user | Admin, Manager, Staff |
| Project type | Internal Project | Project Manager/ Scrum Master | Tuan, Le Ha Duc |
| Project category | Workforce Scheduling & Personnel Management | Business Domain | F&B Workforce Management |
| Application type | Web Management Application + Staff Mobile App |  |  |

Table 1: Project Description

Smart Scheduling is a Web and Mobile workforce-management system designed for one small or medium F&B store. The system supports three operational roles: Admin, Manager, and Staff. Laravel and Microsoft SQL Server form the always-available core for authentication/RBAC, employee and skill management, weekly availability, shift requirements, manual scheduling, leave and shift-change workflows, GPS attendance, timesheets, dashboards, reports, notifications, and audit history. A separate Python/FastAPI Scheduling Service uses Google OR-Tools CP-SAT to generate constraint-aware Draft Schedules. An optional AI Service explains verified backend data and supports decisions but does not directly publish schedules or modify authoritative production data. Manager confirmation remains mandatory for official schedule changes.

1.2. SCOPE AND PURPOSE

This document defines the management plan for the Smart Scheduling project while preserving the approved Capstone scope and delivery structure. It describes project objectives, assumptions, constraints, risks, development process, quality strategy, testing approach, schedule, resources, infrastructure, training, team organization, communication, configuration management, and security. The implementation scope is limited to one F&B store. Multi-store and multi-tenant operation, full payroll/tax processing, recruitment, continuous GPS tracking, and autonomous AI employment decisions are outside the MVP and may be considered future scope.

1.3. ASSUMPTIONS AND CONSTRAINT

| No. | Description | Note |
| --- | --- | --- |
| Assumptions |  |  |
| 1 | Requirements and details may be refined after Mentor or review-panel feedback without changing the approved single-store product boundary. | Scope |
| 2 | Web and Mobile clients communicate through the Laravel REST API; optional Scheduling and AI services are invoked through controlled backend workflows. | External Interfaces |
| 3 | The five-member student team has limited capacity and may need to re-prioritize optional AI/advanced analytics work when Sprint capacity is insufficient. | Resources |
| 4 | The target validation dataset is approximately 20-30 Staff members for one weekly scheduling period. | Quality |
| 5 | The official Capstone window is 26/08/2026-06/12/2026; the detailed team plan includes preparation work before the official start and targets the final release package by 27/11/2026. | Schedule |
| Constraints |  |  |
| 1 | The implementation must remain within the approved Smart Scheduling User Stories, Product Backlog, and Proposal scope. | Scope |
| 2 | The MVP supports one F&B store only; multi-store, cross-store assignment, and tenant isolation are deferred to Future Scope. | Scope |
| 3 | React Web is used for Admin/Manager and a React Native Mobile App is used for Staff; both access business data only through Laravel REST APIs. | Architecture |
| 4 | The project is implemented by five students using open-source/free or academically available tools whenever practical. | Resources/Budget |
| 5 | Laravel + Microsoft SQL Server are the core system of record. Failure of Scheduling Service or AI Service must not stop manual scheduling, leave, attendance, timesheet, dashboard, or reporting functions. | Reliability |
| 6 | The Scheduling Engine uses a configurable time limit with a target of about 15 seconds for the agreed 20-30 Staff weekly dataset; valid generated schedules must have zero hard-constraint violations. | Quality |
| 7 | Open Shift Claim/replacement assignment must be concurrency-safe so a single vacancy cannot be assigned successfully to more than one Staff member. | Data Integrity |
| 8 | Authentication uses secure token/session handling and RBAC. GPS is collected only during attendance events. AI is advisory only and Manager retains final operational decision authority. | Security/Privacy |

Table 2: Assumptions and Constraints

1.4. PROJECT OBJECT

1.4.1. STANDARD OBJECTIVES

| Metrics | Unit | Committed | Committed | Note |
| --- | --- | --- | --- | --- |
| Standard Date | dd-mm-yyyy | 26-08-2026 | 26-08-2026 | Official Capstone start |
| End Date | dd-mm-yyyy | 06-12-2026 | 06-12-2026 | Official Capstone end |
| Duration | Elapsed days | 103 | 103 | Official project window |
| Maximum Team Size | Person | 5 | 5 |  |
| Planned Active Schedule | Elapsed days | 99 | 99 | 21/08/2026-27/11/2026 including preparation |
| Number of work hours per day for one engineer | Person-hour | 3 | 3 | Planning assumption |

Table 3: Standard Objectives

1.4.2. SPECIFIC OBJECTIVES

Specific: Build Smart Scheduling as a Web and Mobile workforce-management solution for one F&B store. Implement Admin/Manager/Staff RBAC; employee, skill, contract and pay-rate data; weekly availability; shift and staffing requirements; manual scheduling; constraint-based automatic scheduling with Python/FastAPI + OR-Tools; Manager review and publish; leave, shift swap and open-shift/replacement handling; GPS check-in/check-out; attendance-to-timesheet processing; dashboard/reporting; notifications; and an optional AI Assistant that only explains verified data.

Measurable: Core APIs remain usable when Scheduling or AI Service is stopped; unauthorized role access is rejected; automatic schedules contain zero hard-constraint violations; the solver uses a configurable target time limit of about 15 seconds for a weekly dataset of approximately 20-30 Staff; insufficient staffing is returned as explicit unfilled demand instead of silently breaking hard constraints; only one Staff can successfully claim one open vacancy; and core API P95 is targeted below 500 ms in the agreed test environment.

Achievable: The team uses React.js for the management Web application, React Native (JavaScript/JSX) for the Staff Mobile App, Laravel/PHP for the core REST API, Microsoft SQL Server for authoritative relational data, Redis for queue/cache, Python/FastAPI + Google OR-Tools CP-SAT for scheduling, and Docker/Docker Compose for service isolation. The architecture allows the team to implement and test the core workflow first, while Scheduling and AI remain independent enhancement services.

Relevant: The project addresses recurring F&B workforce problems involving changing part-time availability, skill requirements, staffing shortages, sudden leave, attendance verification, actual working-hour calculation, and manual schedule maintenance. The system is intentionally narrower than a full HRM/ERP and focuses on the end-to-end shift-operation workflow.

Time-bound: Work is organized into four Sprints. Sprint 1 establishes core access, employee/skill, availability and shift requirements; Sprint 2 implements automatic scheduling, review and publishing; Sprint 3 implements leave/swap/open-shift/replacement and GPS attendance; Sprint 4 implements timesheets, dashboard/reporting, optional AI support, integration and hardening. The detailed team plan targets final release preparation by 27/11/2026 within the official Capstone window ending 06/12/2026.

1.5. CRITICAL DEPENDENCIES

The progress and success of Smart Scheduling depend on the following technical and operational factors:

Technical Dependencies:

- Scheduling Service: Python/FastAPI and Google OR-Tools CP-SAT must correctly consume a validated scheduling snapshot and return Draft assignments plus shortage/conflict metadata within the configured time limit.

- Core API and data contract: React Web and the Staff Mobile App depend on stable Laravel REST contracts. Laravel remains the owner of validation, official schedule state, attendance, timesheet, reporting, and database writes.

- Redis / optional integrations: Redis supports asynchronous jobs and cache. External LLM availability affects only the optional AI Assistant; AI failure must not block core functions. Push-notification delivery may use Firebase Cloud Messaging or an equivalent service [Cần xác nhận lại].

Operational Dependencies:

- Supervising Instructor (PhD. Vu, Truong Tien): availability for requirement clarification, document review, milestone feedback, and technical guidance.

- Development infrastructure: reliable access to GitHub, Docker, Microsoft SQL Server, Redis, development devices, test smartphones/location services, and agreed collaboration tools throughout implementation and testing.

1.6. PROJECT RISK

| Risk | Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Scheduling estimation | OR-Tools constraint modeling may take longer than expected because the team is still building optimization experience. | 5 | 4 | Prototype hard constraints early, keep small reference datasets, review the model with the Mentor, and separate must-have constraints from later soft objectives. |
| Sprint workload distribution | Web, Mobile, Laravel, Scheduling and optional AI work may overload one Sprint. | 4 | 4 | Use a strict MVP cut line, track velocity weekly, reallocate work, and defer optional AI/advanced analytics when core delivery is at risk. |
| Service integration | Laravel, Redis, FastAPI Scheduling and Mobile/Web clients can drift in request/response formats. | 4 | 4 | Define versioned API/job contracts early, use mocks and contract tests, and integrate continuously rather than at the end. |
| Scheduling infeasibility | Real input may not have enough eligible Staff to fill every shift. | 5 | 5 | Keep safety/policy rules hard, model staffing shortage with high-penalty slack/unfilled variables, and return best feasible Draft plus shortage details. |
| Concurrency on Open Shift | Two Staff may try to accept the same vacancy at nearly the same time. | 4 | 5 | Use transactions/Optimistic Locking, Open Shift status/version checks, uniqueness constraints, and final eligibility revalidation before confirmation. |
| Optional service failure | Scheduling or AI service may be slow, unavailable, or resource intensive. | 4 | 5 | Use asynchronous Redis jobs, timeout, bounded retry/circuit breaker, health checks, separate containers/resource limits, and graceful-degradation tests. |
| GPS quality/privacy | GPS may be inaccurate/spoofed and location data is sensitive. | 3 | 4 | Validate geofence, accuracy and server time; collect location only at attendance events; flag exceptions for Manager review and avoid continuous tracking. |

Table 4: Project Risk

2. PROJECT DEVELOPMENT APPROACH

2.1. TECHNICAL PROCESS

The team applies Agile Scrum to deliver Smart Scheduling incrementally. The technical stack is React.js for the Admin/Manager Web application, a React Native Mobile App for Staff, Laravel/PHP for the core REST API and business rules, Microsoft SQL Server for authoritative data, Redis for queue/cache, Python/FastAPI + Google OR-Tools CP-SAT for the independent Scheduling Service, and an optional AI Service for verified-data explanation. Docker/Docker Compose provides isolated local/demo services, while GitHub and Trello/Jira support configuration and task management.

2.1.1. REASON FOR SELECTING

Smart Scheduling combines workforce-management business rules with Web/Mobile development, asynchronous jobs, constraint optimization, concurrency control, GPS attendance, and an optional LLM integration. These areas have different technical risks and can change after test data and Mentor feedback. An iterative method lets the team validate the core workflow and interfaces early rather than locking every design decision before implementation.

Scrum is selected because the five-member student team can organize work into four focused Sprints, review usable increments frequently, and re-prioritize optional features without destabilizing the core. The project therefore implements Laravel/Microsoft SQL Server core capabilities first, integrates the OR-Tools Scheduling Service through an explicit contract, and treats AI as a later enhancement. This supports graceful degradation: the store workflow remains usable even if optional intelligent services are unavailable.

2.1.2 AGILE METHODOLOGY

Agile is used to manage requirement and technology uncertainty through short iterations, frequent feedback, incremental integration, and continuous testing.

Each Sprint produces a testable increment and includes planning, design, implementation, integration, testing, review, and retrospective activities. This approach is particularly important for validating Laravel-to-FastAPI scheduling contracts, Mobile GPS attendance behavior, and concurrency-sensitive Open Shift workflows before final integration.

Changes are managed through the Product Backlog and reviewed against the approved single-store scope, Sprint capacity, architecture boundaries, test impact, and final delivery date. Optional AI or advanced enhancements are the first candidates for deferral if they threaten core scope.

2.1.3. SCRUM PROCESS

Figure 1: General Scrum Process

Applying Scrum brings several benefits to the project. Smart Scheduling formally assigns Hien, Le Tran Thanh as Product Owner. The Product Owner maintains and prioritizes the Product Backlog, clarifies requirements and Acceptance Criteria, and reviews completed increments with the team and Mentor. The Scrum Master facilitates Scrum events, tracks impediments, and coordinates delivery without replacing the Product Owner's product-prioritization responsibility.

- The project can easily adapt to change.

- Problems, such as conflicting scheduling constraints, are identified early.

- Managers and Staff (end users) get to see the most valuable features first.

- Delivered work better fits the actual needs of Managers and Staff.

- Improved productivity through focused, time-boxed work.

- Ability to maintain a predictable delivery schedule across 4 Sprints.

2.2. REQUIREMENT CHANGE MANAGEMENT

2.2.1 STRATEGY FOR MEETING QUALITY OBJECTIVES

| Strategy | Expected Benefits |
| --- | --- |
| Apply code standards per component: JavaScript/React conventions, Laravel/PSR conventions, Python/PEP8 for Scheduling/AI services, SQL/database conventions, and React Native/JavaScript conventions. | More consistent code reviews, easier maintenance, and lower avoidable defect injection across multiple technology stacks. |
| Group-review high-risk requirements and designs, especially scheduling hard/soft constraints, schedule publish/versioning, Open Shift concurrency, GPS attendance, timesheet calculation, graceful degradation, and AI boundaries. | Detect business-rule and architecture defects before implementation; improve traceability from User Story to test case. |
| Use four-Sprint incremental delivery with automated API/rule tests, Sprint Review, Retrospective, and regression testing of previously completed core functions. | Earlier defect discovery, controlled change, and reduced risk of late cross-service integration failures. |

Table 5: Strategy for meeting quality objectives

2.2.2 QUALITY CONTROL

| Review Item | Type of Review | Reviewer | When |
| --- | --- | --- | --- |
| Project Plan | Group review | Mentor | End of the Initiation stage |
| Project Schedule | Group review | Mentor |  |
| Product Backlog, User Story | Group review | Mentor | End of 90% of requirements |
| Design Document | Group review | Mentor | End of 90% of design |
| Sprint Backlog | One-person review | Scrum Master | Beginning of each sprint |
| Test case | Group review | Mentor | Before execution / end of detailed test design |
| Code | Group review | Mentor | After coding for the first few programs |

Table 6: Quality Control

2.2.3 MEASUREMENT PROGRAM

| Data to be collected | Pursore | Responsible | When |
| --- | --- | --- | --- |
| Size: backlog items / API endpoints / test cases | Track delivered scope and implementation growth | Scrum Master / Team | End of each Sprint |
| Effort: person-hours / completed tasks | Compare plan with actual effort and support workload balancing | Team Members | Daily / weekly |
| Quality: defects, failed tests, hard-constraint violations | Evaluate product correctness and regression risk | Team Members | After each test run |
| Schedule / service performance | Control Sprint progress and verify API/solver targets | Scrum Master / Team | Weekly and at Sprint end |

Table 7: Measurement program

2.3 UNIT TESTING STRATEGY

Unit Testing is performed separately for the major Smart Scheduling components because the project spans multiple technology stacks and contains high-risk business logic. Priority is given to Laravel authorization/business rules, OR-Tools hard constraints and objective behavior, attendance/timesheet calculations, Open Shift concurrency checks, and failure handling for optional services.

Main unit-level tools/frameworks are:

- Core Backend (Laravel): PHPUnit/Pest tests for authentication, RBAC, validation, schedule/leave/attendance/timesheet rules, transactions, and API services.

- Scheduling Service (Python/FastAPI + OR-Tools): pytest/unittest tests using deterministic scheduling datasets to verify hard constraints, shortage handling, time limits, and result metadata.

- Web/Mobile clients: React tests for critical components/state handling and React Native component and integration tests for availability, schedule, request, attendance, GPS/location, and notification flows.

- Supporting services: tests for Redis job idempotency/status handling and AI adapter boundaries; AI response wording is not treated as authoritative business logic.

Each business rule is tested independently where possible, then re-tested through API/integration scenarios. This reduces coupling and makes failures easier to isolate across Laravel, Python, Web, Mobile, Redis, and external services.

The team's Unit Testing process consists of 4 steps:

- Create test cases from User Stories, Acceptance Criteria, scheduling constraints, and Business Rules.

- Review/Rework test cases, especially high-risk authorization, scheduling, concurrency, GPS, and timesheet scenarios.

- Baseline the approved test dataset and expected results for repeatable regression testing.

- Execute tests before merge/release; log defects, correct them, and re-run affected regression suites.

2.4. INTEGRATION TESTING STRATEGY

Integration Testing validates the dependency direction Web/Mobile -> Laravel REST API -> Microsoft SQL Server/Redis and Laravel -> optional Scheduling/AI services. Clients must never directly access the database or optional internal services.

- Prepare the Integration Test Plan and prioritize end-to-end flows: Availability -> Shift Requirements -> Auto/Manual Scheduling -> Draft Review -> Publish -> Notification -> GPS Attendance -> Timesheet -> Report; plus Leave/Swap/Open Shift replacement flows.

- Design scenarios for Laravel-FastAPI job contracts, Redis job states, Schedule Draft persistence, Open Shift concurrency, GPS validation, notification retries, and optional AI permission-filtered requests.

- Execute API and service integration tests using Postman/automated tests and Docker environments; record format errors, authorization failures, timeouts, race conditions, and inconsistent data states.

- Re-test fixed defects and regression-test dependent workflows, especially published schedule versions, attendance/timesheets, and replacement assignments.

- Repeat integration and graceful-degradation tests until each Sprint increment is stable enough for Sprint Review.

2.5. SYSTEM TESTING STRATEGY

System Testing is performed by the five project members because there is no dedicated QA role. Testing covers the complete Web/Mobile workflow and verifies that role behavior and business state remain consistent across services.

Within the Capstone schedule, the team prioritizes functional testing, authorization/security checks, scheduling correctness, concurrency tests, GPS attendance scenarios, timesheet calculation, basic performance tests, and graceful-degradation tests. A valid generated schedule must have zero hard-constraint violations; core API and solver performance are measured in the agreed test environment.

The team uses free/open-source or academically available tools such as PHPUnit/Pest, pytest, React/Mobile test tools, Postman, Microsoft SQL Server, Redis, GitHub, and Docker/Docker Compose.

Because the team is still developing experience with optimization, concurrency and distributed-service testing, complex cases are based on small deterministic datasets and reviewed with the Mentor when needed.

The testing budget uses existing student devices and free tools. No paid enterprise QA platform is required for the planned MVP.

3. ESTIMATION

3.1. SIZE

Size and scope baselines are defined by C1SE.57_PROPOSAL_Smart_Scheduling_v1.3.docx, C1SE.57_USER_STORY_Smart_Scheduling_v1.1.docx, and C1SE.57_PRODUCT_BACKLOG_Smart_Scheduling_v1.1.docx. The project tracks backlog items, APIs, test cases and completed Sprint scope rather than treating KLOC alone as the primary size measure.

3.2. SCHEDULE

3.2.1 PROJECT MILESTONES & DELIVERABLES

| No | Milestone | Time | Product |
| --- | --- | --- | --- |
| 1 | Initial | 21/08/2026-27/08/2026 | Requirements baseline; Proposal |
| 2 | Start Up | 28/08/2026-31/08/2026 | Kick-off; User Story; Product Backlog; Project Plan; Architecture Design; document review |
| 2.1 | Sprint 1 | 01/09/2026-21/09/2026 | Authentication/RBAC; Employee & Skill; Availability; Shift/Staffing Requirements; Core Web/Mobile foundation |
| 2.2 | Sprint 2 | 22/09/2026-12/10/2026 | OR-Tools Scheduling Service; SchedulingRun jobs; Draft/Manual Review; Publish/Versioning; Notifications |
| 2.3 | Sprint 3 | 13/10/2026-02/11/2026 | Leave; Shift Swap; Open Shift/Replacement; concurrency control; GPS Check-in/Check-out |
| 2.4 | Sprint 4 | 03/11/2026-23/11/2026 | Timesheet; Dashboard; PDF/Excel reports; optional AI Assistant; monitoring; integration/system testing |
| 3 | Project Retrospective Meeting | 24/11/2026 | Project review; remaining risks/issues; final-release readiness |
| 4 | Final Release | 25/11/2026-27/11/2026 | Final system; deployment/demo; test report; final documentation package |

Table 9: Project Milestone & Deliverables

3.2.2. WORK BREAKDOWN STRUCTURE

Figure 2: Work Breakdown Structure

3.2.3 DETAILED SCHEDULE

Table 10: Detail schedule

| No. | Task Name | Duration (Effort) | Start | Finish | Assign To |
| --- | --- | --- | --- | --- | --- |
| 1 | Initial | 7 Days | 21/08/2026 | 27/08/2026 | All |
| 1.1 | Gathering Requirement | 4 Days | 21/08/2026 | 24/08/2026 | All |
| 1.1.1 | Get requirements from Mentor | 1 Day | 21/08/2026 | 21/08/2026 | All |
| 1.1.2 | Analyze & baseline requirements | 3 Days | 22/08/2026 | 24/08/2026 | All |
| 1.2 | Create Proposal Document | 3 Days | 25/08/2026 | 27/08/2026 | All |
| 1.2.1 | Product Definition & Business Need | 1 Day | 25/08/2026 | 25/08/2026 | Tuan |
| 1.2.2 | Prior Art & Proposed Solution | 1 Day | 26/08/2026 | 26/08/2026 | Nghia |
| 1.2.3 | Master Plan & Project Schedule | 1 Day | 27/08/2026 | 27/08/2026 | Tuan |
| 2 | Start Up | 4 Days | 28/08/2026 | 31/08/2026 | All |
| 2.1 | Project Kick-off Meeting | 1 Day | 28/08/2026 | 28/08/2026 | All |
| 2.2 | Create Documents | 3 Days | 29/08/2026 | 31/08/2026 | All |
| 2.2.1 | Create User Stories | 1 Day | 29/08/2026 | 29/08/2026 | All |
| 2.2.2 | Create Product Backlog | 1 Day | 29/08/2026 | 29/08/2026 | All |
| 2.2.3 | Create Project Plan | 1 Day | 30/08/2026 | 30/08/2026 | Tuan |
| 2.2.4 | Create Architecture Design Document | 2 Days | 30/08/2026 | 31/08/2026 | Luc, Nghia |
| 2.2.5 | Review Documents / v1.1 Update | 1 Day | 31/08/2026 | 31/08/2026 | All |
| 3 | Development | 84 Days | 01/09/2026 | 23/11/2026 | All |
| 3.1 | Sprint 1 - Core Access & Workforce Setup | 21 Days | 01/09/2026 | 21/09/2026 | All |
| 3.1.1 | Sprint Planning Meeting | 1 Day | 01/09/2026 | 01/09/2026 | All |
| 3.1.2 | Create Sprint Backlog & Test Plan | 1 Day | 02/09/2026 | 02/09/2026 | All |
| 3.1.3 | Design | 5 Days | 03/09/2026 | 07/09/2026 | All |
| 3.1.3.1 | Design Web/Mobile Authentication & RBAC | 1 Day | 03/09/2026 | 03/09/2026 | Hien, Tuan |
| 3.1.3.2 | Design Employee / Position / Skill Management | 1 Day | 04/09/2026 | 04/09/2026 | Quan, Nghia |
| 3.1.3.3 | Design Staff Weekly Availability | 1 Day | 05/09/2026 | 05/09/2026 | Hien, Luc |
| 3.1.3.4 | Design Shift & Staffing Requirements | 1 Day | 06/09/2026 | 06/09/2026 | Quan |
| 3.1.3.5 | Design Core Database/API & Redis/Docker foundation | 2 Days | 06/09/2026 | 07/09/2026 | Tuan, Nghia, Luc |
| 3.1.4 | Database Design / Migration baseline | 1 Day | 08/09/2026 | 08/09/2026 | Nghia |
| 3.1.5 | Coding | 9 Days | 09/09/2026 | 17/09/2026 | All |
| 3.1.5.1 | [Back-end] Authentication & RBAC | 2 Days | 09/09/2026 | 10/09/2026 | Tuan |
| 3.1.5.2 | [Web] Admin/Manager authentication shell | 2 Days | 09/09/2026 | 10/09/2026 | Hien |
| 3.1.5.3 | [Mobile] Staff authentication/profile shell | 2 Days | 09/09/2026 | 10/09/2026 | Luc |
| 3.1.5.4 | [Back-end] Employee / Skill / Contract basics | 3 Days | 11/09/2026 | 13/09/2026 | Nghia |
| 3.1.5.5 | [Web] Employee / Skill management | 3 Days | 11/09/2026 | 13/09/2026 | Quan |
| 3.1.5.6 | [Back-end] Availability & scheduling periods | 2 Days | 14/09/2026 | 15/09/2026 | Tuan |
| 3.1.5.7 | [Mobile] Weekly availability | 2 Days | 14/09/2026 | 15/09/2026 | Hien, Luc |
| 3.1.5.8 | [Web/Back-end] Shift & staffing requirements | 2 Days | 16/09/2026 | 17/09/2026 | Quan, Nghia |
| 3.1.5.9 | Redis/Queue/Docker baseline | 1 Day | 17/09/2026 | 17/09/2026 | Luc |
| 3.1.6 | Testing & Bug Fixing | 3 Days | 18/09/2026 | 20/09/2026 | All |
| 3.1.7 | Release Sprint 1 & Retrospective | 1 Day | 21/09/2026 | 21/09/2026 | All |
| 3.2 | Sprint 2 - Scheduling Engine & Publish Flow | 21 Days | 22/09/2026 | 12/10/2026 | All |
| 3.2.1 | Sprint Planning Meeting | 1 Day | 22/09/2026 | 22/09/2026 | All |
| 3.2.2 | Create Sprint Backlog & Test Plan | 1 Day | 23/09/2026 | 23/09/2026 | All |
| 3.2.3 | Design | 5 Days | 24/09/2026 | 28/09/2026 | All |
| 3.2.3.1 | Design OR-Tools hard/soft constraint model | 2 Days | 24/09/2026 | 25/09/2026 | Luc |
| 3.2.3.2 | Design SchedulingRun job/API contract | 1 Day | 26/09/2026 | 26/09/2026 | Tuan, Luc |
| 3.2.3.3 | Design Manager schedule review/manual edit UI | 1 Day | 27/09/2026 | 27/09/2026 | Hien |
| 3.2.3.4 | Design publish/versioning & Staff notification flow | 1 Day | 28/09/2026 | 28/09/2026 | Quan |
| 3.2.4 | Database Update for Scheduling | 1 Day | 29/09/2026 | 29/09/2026 | Nghia |
| 3.2.5 | Coding | 7 Days | 30/09/2026 | 06/10/2026 | All |
| 3.2.5.1 | Scheduling Service FastAPI + OR-Tools CP-SAT | 6 Days | 30/09/2026 | 05/10/2026 | Luc |
| 3.2.5.2 | Laravel SchedulingRun / Redis orchestration | 3 Days | 30/09/2026 | 02/10/2026 | Tuan |
| 3.2.5.3 | Manager Draft Schedule review/manual edit | 3 Days | 01/10/2026 | 03/10/2026 | Hien, Tuan |
| 3.2.5.4 | Publish / versioning / constraint revalidation | 2 Days | 04/10/2026 | 05/10/2026 | Quan, Nghia |
| 3.2.5.5 | Unfilled-shift/conflict metadata & status UI | 2 Days | 05/10/2026 | 06/10/2026 | Luc, Hien |
| 3.2.5.6 | Schedule notifications to Staff | 2 Days | 05/10/2026 | 06/10/2026 | Quan, Tuan |
| 3.2.6 | Testing, Performance & Bug Fixing | 5 Days | 07/10/2026 | 11/10/2026 | All |
| 3.2.7 | Release Sprint 2 & Retrospective | 1 Day | 12/10/2026 | 12/10/2026 | All |
| 3.3 | Sprint 3 - Change Handling & GPS Attendance | 21 Days | 13/10/2026 | 02/11/2026 | All |
| 3.3.1 | Sprint Planning Meeting | 1 Day | 13/10/2026 | 13/10/2026 | All |
| 3.3.2 | Create Sprint Backlog & Test Plan | 1 Day | 14/10/2026 | 14/10/2026 | All |
| 3.3.3 | Design | 5 Days | 15/10/2026 | 19/10/2026 | All |
| 3.3.3.1 | Design Leave / Emergency Leave workflow | 1 Day | 15/10/2026 | 15/10/2026 | Hien |
| 3.3.3.2 | Design Direct Shift Swap workflow | 1 Day | 16/10/2026 | 16/10/2026 | Quan |
| 3.3.3.3 | Design Open Shift / Replacement & locking | 1 Day | 17/10/2026 | 17/10/2026 | Nghia |
| 3.3.3.4 | Design eligible replacement fallback filtering | 1 Day | 18/10/2026 | 18/10/2026 | Tuan, Luc |
| 3.3.3.5 | Design GPS Attendance / geofence workflow | 1 Day | 19/10/2026 | 19/10/2026 | Luc, Quan |
| 3.3.4 | Database Update for Requests/Attendance | 1 Day | 20/10/2026 | 20/10/2026 | Nghia |
| 3.3.5 | Coding | 8 Days | 21/10/2026 | 28/10/2026 | All |
| 3.3.5.1 | Leave request & Manager approval | 3 Days | 21/10/2026 | 23/10/2026 | Tuan, Hien |
| 3.3.5.2 | Direct Shift Swap with revalidation | 3 Days | 21/10/2026 | 23/10/2026 | Quan, Nghia |
| 3.3.5.3 | Open Shift claim / replacement workflow | 3 Days | 24/10/2026 | 26/10/2026 | Quan, Nghia |
| 3.3.5.4 | Transaction / Optimistic Locking protection | 2 Days | 24/10/2026 | 25/10/2026 | Nghia |
| 3.3.5.5 | Laravel eligible replacement fallback | 2 Days | 26/10/2026 | 27/10/2026 | Tuan |
| 3.3.5.6 | [Back-end] GPS Check-in/Check-out validation | 2 Days | 27/10/2026 | 28/10/2026 | Tuan |
| 3.3.5.7 | [Mobile] GPS Check-in/Check-out UI | 2 Days | 27/10/2026 | 28/10/2026 | Luc |
| 3.3.6 | Testing & Bug Fixing | 4 Days | 29/10/2026 | 01/11/2026 | All |
| 3.3.7 | Release Sprint 3 & Retrospective | 1 Day | 02/11/2026 | 02/11/2026 | All |
| 3.4 | Sprint 4 - Timesheet, Reporting & Integration | 21 Days | 03/11/2026 | 23/11/2026 | All |
| 3.4.1 | Sprint Planning Meeting | 1 Day | 03/11/2026 | 03/11/2026 | All |
| 3.4.2 | Create Sprint Backlog & Test Plan | 1 Day | 04/11/2026 | 04/11/2026 | All |
| 3.4.3 | Design | 5 Days | 05/11/2026 | 09/11/2026 | All |
| 3.4.3.1 | Design attendance reconciliation & Timesheet | 1 Day | 05/11/2026 | 05/11/2026 | Quan, Nghia |
| 3.4.3.2 | Design Dashboard / labor summaries | 1 Day | 06/11/2026 | 06/11/2026 | Hien |
| 3.4.3.3 | Design PDF/Excel reports & notifications | 1 Day | 07/11/2026 | 07/11/2026 | Quan |
| 3.4.3.4 | Design optional AI Assistant boundaries/API | 1 Day | 08/11/2026 | 08/11/2026 | Luc |
| 3.4.3.5 | Design service health / graceful degradation tests | 1 Day | 09/11/2026 | 09/11/2026 | Tuan |
| 3.4.4 | Database Update for Timesheet/AI/Monitoring | 1 Day | 10/11/2026 | 10/11/2026 | Nghia |
| 3.4.5 | Coding | 8 Days | 11/11/2026 | 18/11/2026 | All |
| 3.4.5.1 | Attendance reconciliation & correction | 2 Days | 11/11/2026 | 12/11/2026 | Tuan, Quan |
| 3.4.5.2 | Timesheet calculation / review / approval | 3 Days | 11/11/2026 | 13/11/2026 | Nghia, Hien |
| 3.4.5.3 | Dashboard data aggregation & UI | 3 Days | 14/11/2026 | 16/11/2026 | Nghia, Hien |
| 3.4.5.4 | PDF/Excel operational reports | 2 Days | 14/11/2026 | 15/11/2026 | Tuan, Quan |
| 3.4.5.5 | Notifications / device tokens | 2 Days | 16/11/2026 | 17/11/2026 | Quan, Luc |
| 3.4.5.6 | Optional AI Service / verified-data explanation | 3 Days | 16/11/2026 | 18/11/2026 | Luc |
| 3.4.5.7 | Service health / monitoring & failure states | 2 Days | 17/11/2026 | 18/11/2026 | Tuan |
| 3.4.6 | Integration/System Testing & Refinement | 4 Days | 19/11/2026 | 22/11/2026 | All |
| 3.4.7 | Release Sprint 4 & Retrospective | 1 Day | 23/11/2026 | 23/11/2026 | All |
| 4 | Project Retrospective Meeting | 1 Day | 24/11/2026 | 24/11/2026 | All |
| 5 | Final Release | 3 Days | 25/11/2026 | 27/11/2026 | All |
| 5.1 | Final Testing & Bug Fixing | 1 Day | 25/11/2026 | 25/11/2026 | All |
| 5.2 | Deployment / Demo Preparation | 1 Day | 26/11/2026 | 26/11/2026 | All |
| 5.3 | Final Documentation & Deliverables | 1 Day | 27/11/2026 | 27/11/2026 | All |
| Total | Planned Team Work Schedule | 99 Days | 21/08/2026 | 27/11/2026 | All |

3.2.4 Cost

3.2.4.1 Resources

Table 11. Cost Description.

| Description | Amount | Unit |
| --- | --- | --- |
| Number of members | 5 | Person |
| Number of working hours per day | 3 | Hours |
| Number of project days used for cost estimation | 108 | Days |
| Planned person-hours | 1,620 | Hours |
| The cost per member per hour | 2 | USD |
| Working-hour cost | 3,240 | USD |
| Other costs | 500 | USD |
| Total cost estimate | 3,740 | USD |

3.2.4.2 Total Cost Estimate

Table 12. Total Cost.

| No. | Criteria | Price (USD) | Amount (Hours) | Total (USD) |
| --- | --- | --- | --- | --- |
| 1 | Working hour | 2 | 1,620 | 3,240 |
| 2 | Other costs | 500 | - | 500 |
| Total |  |  |  | 3,740 |

Explain:

- Planned person-hours = 5 members × 3 hours/day × 108 project days = 1,620 hours.

- Working-hour cost = 1,620 hours × 2 USD/hour = 3,240 USD.

- Other costs = 5 members × 100 USD/person = 500 USD, aligned with the Proposal cost baseline.

- Total Cost Estimate = 3,240 USD + 500 USD = 3,740 USD.

3.4. RESOURCE

Specified as in the section Project Team

3.5. INFRASTRUCTURE

| Category | Tool / Product | Purpose | Readiness Phase | Notes |
| --- | --- | --- | --- | --- |
| Development Environment | Visual Studio Code | Develop Web/Mobile/Core/Service source code | Inception Phase |  |
|  | React.js | Admin/Manager Web frontend | Inception Phase |  |
|  | React Native (JavaScript/JSX) | Staff Mobile App | Inception Phase | Final selected mobile framework |
|  | Laravel / PHP | Core REST API and business rules | Inception Phase |  |
|  | Microsoft SQL Server | Authoritative relational database | Inception Phase |  |
|  | Redis | Queue/cache for jobs and notifications | Development Phase |  |
|  | Python + FastAPI | Scheduling and optional AI service layer | Development Phase |  |
|  | Google OR-Tools CP-SAT | Constraint-based automatic scheduling | Development Phase |  |
| Hardware & Software | Laptop / Smartphone | Development, Web/Mobile and GPS testing | Inception Phase | Personal/team devices |
|  | Docker / Docker Compose | Reproducible isolated service environment | Development Phase |  |
| Other Tools | GitHub | Version control, branch/review workflow | Inception Phase |  |
|  | Trello / Jira | Task and Sprint tracking | Inception Phase |  |
|  | Figma | Web/Mobile UI/UX design | Inception Phase |  |
|  | Draw.io | Architecture and system diagrams | Inception Phase |  |
|  | Postman | REST/internal API testing | Development Phase |  |
|  | PHPUnit/Pest + pytest + client tests | Automated unit/regression testing | Development Phase |  |

Table 11: Infrastructure

3.6. TRAINING PLAN

| Training Category | Content | Participants | Duration | Exemption Criteria |
| --- | --- | --- | --- | --- |
| Technical | React.js and responsive Web UI | Web developers | 3 days | If already proficient |
|  | Laravel/PHP REST API, RBAC, transactions | Backend developers | 3 days | If already proficient |
|  | Microsoft SQL Server + Redis + database/concurrency design | Backend/database members | 3 days | If already proficient |
|  | Python/FastAPI + OR-Tools CP-SAT | Scheduling members | 5 days | If already proficient |
|  | React Native + GPS/location APIs | Mobile developers | 3 days | If already proficient |
|  | AI/LLM API boundaries and privacy | AI/integration members | 2 days | If already proficient |
| Process | Agile Scrum | All members | 4 hours | If already trained |
| Tools | Git/GitHub + Docker | All members | 4 hours | If already proficient |
| Design | Figma / Draw.io | Designers/analysts | 2 hours | If already experienced |
| Testing | Postman, unit testing, concurrency & graceful-degradation tests | Developers/Testers | 1 day | If already experienced |

Table 12: Training plan

4. PROJECT ORGANIZATION

4.1. PROJECT TEAM

| Role | Responsibilities | Full Name |
| --- | --- | --- |
| Scrum Master | - Coordinate team activities and Scrum events. - Track Sprint goals, risks and impediments. - Maintain plan/schedule and coordinate with Mentor. - Participate in development and integration. | Tuan, Le Ha Duc |
| Product Owner | - Maintain and prioritize the Product Backlog. - Clarify product requirements and Acceptance Criteria. - Coordinate requirement questions with the Mentor and project stakeholders. - Review Sprint increments and confirm product priorities for subsequent work. | Hien, Le Tran Thanh |
| Team Member | - UI/UX and feature implementation as assigned. - Functional testing. - Support integration, reports and documentation. | Quan, Huynh Van Minh |
| Team Member | - Scheduling/AI/Mobile integration tasks as assigned. - Technical research and testing. - Support deployment and product completion. | Luc, Huynh Vu |
| Team Member | - Backend/database design and implementation as assigned. - Data integrity/concurrency testing. - Support integration and documentation. | Nghia, Le Dinh |
| Mentor | - Guide project execution. - Review requirements, plans, architecture and deliverables. - Support resolution of technical/project issues. - Review product progress. | PhD Vu, Truong Tien |

Table 13: Project team

4.2 PROJECT TEAM

| Full Name | Position |
| --- | --- |
| PhD Vu, Truong Tien | Mentor |
| Tuan, Le Ha Duc | Scrum Master, Team Member |
| Hien, Le Tran Thanh | Product Owner, Team Member |
| Quan, Huynh Van Minh | Team Member |
| Luc, Huynh Vu | Team Member |
| Nghia, Le Dinh | Team Member |

5. COMMUNICATION & REPORTING

| Communication Type | Method / Tool | Frequency / Timing | Information / Content | Participants / Responsible Person |
| --- | --- | --- | --- | --- |
| Project Task Tracking | Trello / Jira / GitHub | Beginning of each Sprint and weekly | Plan, update, and track tasks | Scrum Master |
| Task Assignment | Trello / Jira, Team meeting | Weekly / As needed | Assign tasks to each member | Scrum Master |
| Kick-off Meeting | In-person / Google Meet / Discord | Initiation Phase | Introduce project, review Project Plan, identify risks, and align on responsibilities | Entire team |
| Regular Team Meeting | Zalo / Discord / In-person / Google Meet | Periodically during development | Completed tasks, tasks in progress, challenges, and solutions | Entire team |
| Sprint Planning Meeting | In-person / Google Meet / Messenger | Beginning of each Sprint | Analyze requirements, define features, plan, and divide tasks | Entire team |
| Sprint Review Meeting | In-person / Google Meet | End of each Sprint | Review completed features, testing, documentation, and outstanding issues | Entire team |
| Sprint Retrospective | In-person / Google Meet | End of each Sprint | Evaluate what went well, issues encountered, and improvements for the next Sprint | Entire team |
| Communication with Mentor | Zalo / In-person / Google Meet | As needed or upon significant changes | Review scope, backlog, architecture, quality, progress, risks, and technical issues | Team Members, Mentor |
| Project Progress Review | Team meeting | Weekly | Project status, blockers, test results, scheduling-rule questions, and items needing clarification | Team Members, Mentor |
| Milestone Review | Milestone Review Meeting | End of each phase | Evaluate objectives, quality, progress, workload, and update the plan for the next phase | Team Members, Mentor |

Table 14: Communication & Reporting

6. CONFIGURATION MANAGEMENT

Configuration management uses Git/GitHub for source code, version-controlled documentation for baselined project artifacts, database migrations for schema changes, Docker/Docker Compose for reproducible environments, and environment-variable templates for service configuration. Main configuration items include Web, Mobile, Laravel Core, Scheduling Service, optional AI Service, database schema/migrations, API/job contracts, test datasets, deployment files, and approved project documents.

Changes are recorded through branches/pull requests or equivalent team review, linked to backlog tasks where practical, and merged only after relevant tests/review. Published schedule data and approved timesheets are application business records rather than source-control artifacts; their integrity is protected through database transactions, version/audit information, and controlled authorization.

7. SECURITY ASPECTS

- Passwords are stored using one-way adaptive hashing; protected APIs require authenticated tokens/sessions and server-side RBAC checks for Admin, Manager, and Staff. Client-side UI restrictions are not treated as authorization controls.

- Microsoft SQL Server and internal services are not exposed directly to Web/Mobile clients. Service endpoints use controlled network access, validation, rate/timeout protections, request tracing where applicable, and secrets are stored outside source code. GPS is collected only at check-in/check-out and only data necessary for an authorized AI request is sent to an external LLM.

- Security and integrity tests include unauthorized-role API calls, employee-record isolation by role, duplicate Open Shift Claim, invalid/tampered attendance inputs, schedule-publish authorization, and graceful-degradation scenarios. AI cannot directly publish schedules, modify official employee records, or make final reward/penalty/pay/promotion decisions.

8. REFERENCES

1. C1SE.57_PROPOSAL_Smart_Scheduling_v1.3.docx - approved scope, architecture, schedule, and quality targets.

2. C1SE.57_USER_STORY_Smart_Scheduling_v1.1.docx and C1SE.57_PRODUCT_BACKLOG_Smart_Scheduling_v1.1.docx - functional baseline and priorities.

3. Scrum Guide / Agile references; Laravel, React, Microsoft SQL Server, Redis, FastAPI, Google OR-Tools, Docker, and React Native documentation.