## Estimate
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 1 - Core Platform Foundation
Development Team: |  | C1SE.57
Start Date: |  | 2026-09-01
End Date: |  | 2026-09-22
On Time
No. | Member Name | Full Name | Estimate |  |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 35 |  |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 34 |  |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 32
4 | Quan | Huỳnh Văn Minh Quân | 33
5 | Luc | Huỳnh Vũ Lực | 21
Total |  |  | 155
SPRINT 1 REPORT | Component | Task Name | Responsible Member | Estimate | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22
Planning
| Planning | Sprint Planning Meeting | Tuan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planning | Create Sprint Backlog & Test Plan | Tuan | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Environment
| Environment | Configure React Web project | Hien | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Environment | Configure Laravel Core API | Tuan | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Environment | Configure React Native (JavaScript/JSX) project | Quan | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Environment | Configure Microsoft SQL Server / Redis / Docker | Luc | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design
| Design | Design Login & RBAC UI | Hien | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Employee / Skill Management UI | Hien | 5 | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Staff Availability UI | Quan | 5 | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Shift Requirement UI | Quan | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database
| Database | Design core database schema | Nghia | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend
| Backend | Implement JWT authentication & RBAC | Tuan | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement Employee / Contract / Skill APIs | Nghia | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement Availability APIs | Tuan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement Shift & Staffing Requirement APIs | Nghia | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Web
| Web | Implement Login / Account screens | Hien | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web | Implement Employee / Skill screens | Hien | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
React Native
| React Native | Implement Staff Login / Profile (React Native) | Quan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| React Native | Implement Weekly Availability registration (React Native) | Quan | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration
| Integration | Connect React Web / React Native to Laravel APIs | Luc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing
| Testing | Unit tests for Auth / RBAC / Employee | Tuan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | API tests for Availability / Shift | Nghia | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | UI functional testing | Hien | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0
| Testing | React Native functional testing | Quan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0
Release
| Release | Bug fixing & Sprint 1 release | Luc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0
|  |  | TOTAL | 155 | 150 | 140.5 | 128.5 | 120 | 110 | 99 | 92 | 85 | 73.5 | 64.5 | 55 | 45.5 | 38 | 30.5 | 25 | 18.5 | 11 | 6 | 4 | 2 | 0 | 0

## Actual
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 1 - Core Platform Foundation
Development Team: |  | C1SE.57
Start Date: |  | 2026-09-01
End Date: |  | 2026-09-22
On Time
No. | Member Name | Full Name | Estimate | Actual |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 35 | 0 |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 34 | 0 |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 32 | 0
4 | Quan | Huỳnh Văn Minh Quân | 33 | 0
5 | Luc | Huỳnh Vũ Lực | 21 | 0
Total |  |  | 155 | 0
SPRINT 1 REPORT | Component | Task Name | Responsible Member | Actual | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22
Planning
| Planning | Sprint Planning Meeting | Tuan |  | 2026-09-01: 3
| Planning | Create Sprint Backlog & Test Plan | Tuan |  | 2026-09-01: 4
Environment
| Environment | Configure React Web project | Hien |  | 2026-09-01: 4
| Environment | Configure Laravel Core API | Tuan |  | 2026-09-01: 4
| Environment | Configure React Native (JavaScript/JSX) project | Quan |  | 2026-09-01: 4
| Environment | Configure Microsoft SQL Server / Redis / Docker | Luc |  | 2026-09-01: 5
Design
| Design | Design Login & RBAC UI | Hien |  | 2026-09-01: 4
| Design | Design Employee / Skill Management UI | Hien |  | 2026-09-01: 5
| Design | Design Staff Availability UI | Quan |  | 2026-09-01: 5
| Design | Design Shift Requirement UI | Quan |  | 2026-09-01: 4
Database
| Database | Design core database schema | Nghia |  | 2026-09-01: 8
Backend
| Backend | Implement JWT authentication & RBAC | Tuan |  | 2026-09-01: 10
| Backend | Implement Employee / Contract / Skill APIs | Nghia |  | 2026-09-01: 10
| Backend | Implement Availability APIs | Tuan |  | 2026-09-01: 8
| Backend | Implement Shift & Staffing Requirement APIs | Nghia |  | 2026-09-01: 8
Web
| Web | Implement Login / Account screens | Hien |  | 2026-09-01: 7
| Web | Implement Employee / Skill screens | Hien |  | 2026-09-01: 9
React Native
| React Native | Implement Staff Login / Profile (React Native) | Quan |  | 2026-09-01: 6
| React Native | Implement Weekly Availability registration (React Native) | Quan |  | 2026-09-01: 9
Integration
| Integration | Connect React Web / React Native to Laravel APIs | Luc |  | 2026-09-01: 8
Testing
| Testing | Unit tests for Auth / RBAC / Employee | Tuan |  | 2026-09-01: 6
| Testing | API tests for Availability / Shift | Nghia |  | 2026-09-01: 6
| Testing | UI functional testing | Hien |  | 2026-09-01: 5
| Testing | React Native functional testing | Quan |  | 2026-09-01: 5
Release
| Release | Bug fixing & Sprint 1 release | Luc |  | 2026-09-01: 8
|  |  | TOTAL | 0 | 2026-09-01: 155

## Chart
Burn down chart Sprint 1
Estimate | Actual | Date
150 |  | 2026-09-01
140.5 |  | 2026-09-02
128.5 |  | 2026-09-03
120 |  | 2026-09-04
110 |  | 2026-09-05
99 |  | 2026-09-06
92 |  | 2026-09-07
85 |  | 2026-09-08
73.5 |  | 2026-09-09
64.5 |  | 2026-09-10
55 |  | 2026-09-11
45.5 |  | 2026-09-12
38 |  | 2026-09-13
30.5 |  | 2026-09-14
25 |  | 2026-09-15
18.5 |  | 2026-09-16
11 |  | 2026-09-17
6 |  | 2026-09-18
4 |  | 2026-09-19
2 |  | 2026-09-20
0 |  | 2026-09-21
0 |  | 2026-09-22