## Estimate
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 2 - Automated Scheduling & Publishing
Development Team: |  | C1SE.57
Start Date: |  | 2026-09-23
End Date: |  | 2026-10-14
On Time
No. | Member Name | Full Name | Estimate |  |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 38 |  |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 34 |  |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 34
4 | Quan | Huỳnh Văn Minh Quân | 29
5 | Luc | Huỳnh Vũ Lực | 66
Total |  |  | 201
SPRINT 2 REPORT | Component | Task Name | Responsible Member | Estimate | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
Planning
| Planning | Sprint Planning Meeting | Tuan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planning | Create Sprint Backlog & Test Plan | Tuan | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design
| Design | Define hard / soft scheduling constraints | Luc | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design SchedulingRun & job status model | Nghia | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Manager schedule review UI | Hien | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Staff published schedule UI (React Native) | Quan | 5 | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduling
| Scheduling | Build FastAPI Scheduling Service | Luc | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scheduling | Implement OR-Tools CP-SAT base model | Luc | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scheduling | Implement hard constraints | Luc | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Scheduling | Implement soft objectives & unfilled-shift slack | Luc | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend
| Backend | Implement SchedulingRun orchestration | Tuan | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement Redis queue / timeout / retry flow | Tuan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement schedule draft / version / publish APIs | Nghia | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement manual schedule validation | Nghia | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Web
| Web | Implement Manager weekly schedule view | Hien | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web | Implement review / manual edit / publish | Hien | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
React Native
| React Native | Implement Staff published schedule view (React Native) | Quan | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notification
| Notification | Implement schedule publish/change notifications | Quan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration
| Integration | Integrate Laravel ↔ Scheduling Service | Tuan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resilience
| Resilience | Implement Scheduling Service health/fallback status | Luc | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing
| Testing | Constraint dataset tests - zero hard violations | Nghia | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Testing | Solver performance test ≤ 15 seconds | Luc | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Testing | Manual scheduling graceful-degradation test | Tuan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0
| Testing | Schedule publish / notification E2E test | Hien | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0
Release
| Release | Bug fixing & Sprint 2 release | Quan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0
|  |  | TOTAL | 201 | 196 | 192 | 186 | 178.5 | 168.5 | 161 | 153 | 139 | 123.5 | 107.5 | 90 | 74 | 60.5 | 47 | 35 | 27 | 19.5 | 9.5 | 4 | 2 | 0 | 0

## Actual
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 2 - Automated Scheduling & Publishing
Development Team: |  | C1SE.57
Start Date: |  | 2026-09-23
End Date: |  | 2026-10-14
On Time
No. | Member Name | Full Name | Estimate | Actual |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 38 | 0 |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 34 | 0 |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 34 | 0
4 | Quan | Huỳnh Văn Minh Quân | 29 | 0
5 | Luc | Huỳnh Vũ Lực | 66 | 0
Total |  |  | 201 | 0
SPRINT 2 REPORT | Component | Task Name | Responsible Member | Actual | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
Planning
| Planning | Sprint Planning Meeting | Tuan |  | 2026-09-23: 3
| Planning | Create Sprint Backlog & Test Plan | Tuan |  | 2026-09-23: 4
Design
| Design | Define hard / soft scheduling constraints | Luc |  | 2026-09-23: 8
| Design | Design SchedulingRun & job status model | Nghia |  | 2026-09-23: 6
| Design | Design Manager schedule review UI | Hien |  | 2026-09-23: 6
| Design | Design Staff published schedule UI (React Native) | Quan |  | 2026-09-23: 5
Scheduling
| Scheduling | Build FastAPI Scheduling Service | Luc |  | 2026-09-23: 10
| Scheduling | Implement OR-Tools CP-SAT base model | Luc |  | 2026-09-23: 14
| Scheduling | Implement hard constraints | Luc |  | 2026-09-23: 12
| Scheduling | Implement soft objectives & unfilled-shift slack | Luc |  | 2026-09-23: 10
Backend
| Backend | Implement SchedulingRun orchestration | Tuan |  | 2026-09-23: 10
| Backend | Implement Redis queue / timeout / retry flow | Tuan |  | 2026-09-23: 8
| Backend | Implement schedule draft / version / publish APIs | Nghia |  | 2026-09-23: 12
| Backend | Implement manual schedule validation | Nghia |  | 2026-09-23: 8
Web
| Web | Implement Manager weekly schedule view | Hien |  | 2026-09-23: 10
| Web | Implement review / manual edit / publish | Hien |  | 2026-09-23: 12
React Native
| React Native | Implement Staff published schedule view (React Native) | Quan |  | 2026-09-23: 9
Notification
| Notification | Implement schedule publish/change notifications | Quan |  | 2026-09-23: 7
Integration
| Integration | Integrate Laravel ↔ Scheduling Service | Tuan |  | 2026-09-23: 8
Resilience
| Resilience | Implement Scheduling Service health/fallback status | Luc |  | 2026-09-23: 6
Testing
| Testing | Constraint dataset tests - zero hard violations | Nghia |  | 2026-09-23: 8
| Testing | Solver performance test ≤ 15 seconds | Luc |  | 2026-09-23: 6
| Testing | Manual scheduling graceful-degradation test | Tuan |  | 2026-09-23: 5
| Testing | Schedule publish / notification E2E test | Hien |  | 2026-09-23: 6
Release
| Release | Bug fixing & Sprint 2 release | Quan |  | 2026-09-23: 8
|  |  | TOTAL | 0 | 2026-09-23: 201

## Chart
Burn down chart Sprint 2
Estimate | Actual | Date
196 |  | 2026-09-23
192 |  | 2026-09-24
186 |  | 2026-09-25
178.5 |  | 2026-09-26
168.5 |  | 2026-09-27
161 |  | 2026-09-28
153 |  | 2026-09-29
139 |  | 2026-09-30
123.5 |  | 2026-10-01
107.5 |  | 2026-10-02
90 |  | 2026-10-03
74 |  | 2026-10-04
60.5 |  | 2026-10-05
47 |  | 2026-10-06
35 |  | 2026-10-07
27 |  | 2026-10-08
19.5 |  | 2026-10-09
9.5 |  | 2026-10-10
4 |  | 2026-10-11
2 |  | 2026-10-12
0 |  | 2026-10-13
0 |  | 2026-10-14