## Estimate
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 3 - Leave, Swap, Open Shift & GPS Attendance
Development Team: |  | C1SE.57
Start Date: |  | 2026-10-15
End Date: |  | 2026-11-05
On Time
No. | Member Name | Full Name | Estimate |  |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 43 |  |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 28 |  |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 46
4 | Quan | Huỳnh Văn Minh Quân | 44
5 | Luc | Huỳnh Vũ Lực | 22
Total |  |  | 183
SPRINT 3 REPORT | Component | Task Name | Responsible Member | Estimate | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05
Planning
| Planning | Sprint Planning Meeting | Tuan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planning | Create Sprint Backlog & Test Plan | Tuan | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design
| Design | Design Leave Request workflow | Hien | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Shift Swap / Open Shift Claim workflow | Quan | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design replacement eligibility rules | Nghia | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design GPS Attendance flow & geofence rules | Quan | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database
| Database | Update leave / swap / open-shift / attendance schema | Nghia | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backend
| Backend | Implement Leave Request & Manager approval APIs | Tuan | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement Shift Swap eligibility validation | Nghia | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Backend | Implement Open Shift Claim / Replacement APIs | Tuan | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Concurrency
| Concurrency | Implement transaction / optimistic locking | Nghia | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Web
| Web | Implement Manager leave / swap approval screens | Hien | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Web | Implement Open Shift management screen | Hien | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
React Native
| React Native | Implement Leave Request UI (React Native) | Quan | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| React Native | Implement Shift Swap / Open Shift Claim UI (React Native) | Quan | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attendance
| Attendance | Implement GPS Check-in / Check-out UI (React Native) | Quan | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Attendance | Implement server-time / geofence validation API | Tuan | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Attendance | Implement Attendance event storage | Nghia | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AI Support
| AI Support | Implement candidate-filter fallback in Laravel | Tuan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| AI Support | Implement optional AI replacement explanation | Luc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notification
| Notification | Implement leave / swap / Open Shift notifications | Luc | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Testing
| Testing | Concurrent Open Shift acceptance test | Nghia | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4.5 | 2.5 | 0 | 0 | 0 | 0 | 0
| Testing | GPS attendance boundary / accuracy tests | Quan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Testing | Leave / Swap / Open Shift E2E tests | Hien | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0
Release
| Release | Bug fixing & Sprint 3 release | Luc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0
|  |  | TOTAL | 183 | 178 | 172.5 | 164.5 | 155 | 147 | 137.5 | 126 | 117 | 103 | 91 | 81.5 | 72 | 60.5 | 51 | 40.5 | 26.5 | 16.5 | 8 | 4 | 2 | 0 | 0

## Actual
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 3 - Leave, Swap, Open Shift & GPS Attendance
Development Team: |  | C1SE.57
Start Date: |  | 2026-10-15
End Date: |  | 2026-11-05
On Time
No. | Member Name | Full Name | Estimate | Actual |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 43 | 0 |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 28 | 0 |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 46 | 0
4 | Quan | Huỳnh Văn Minh Quân | 44 | 0
5 | Luc | Huỳnh Vũ Lực | 22 | 0
Total |  |  | 183 | 0
SPRINT 3 REPORT | Component | Task Name | Responsible Member | Actual | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05
Planning
| Planning | Sprint Planning Meeting | Tuan |  | 2026-10-15: 3
| Planning | Create Sprint Backlog & Test Plan | Tuan |  | 2026-10-15: 4
Design
| Design | Design Leave Request workflow | Hien |  | 2026-10-15: 5
| Design | Design Shift Swap / Open Shift Claim workflow | Quan |  | 2026-10-15: 6
| Design | Design replacement eligibility rules | Nghia |  | 2026-10-15: 6
| Design | Design GPS Attendance flow & geofence rules | Quan |  | 2026-10-15: 6
Database
| Database | Update leave / swap / open-shift / attendance schema | Nghia |  | 2026-10-15: 8
Backend
| Backend | Implement Leave Request & Manager approval APIs | Tuan |  | 2026-10-15: 9
| Backend | Implement Shift Swap eligibility validation | Nghia |  | 2026-10-15: 10
| Backend | Implement Open Shift Claim / Replacement APIs | Tuan |  | 2026-10-15: 10
Concurrency
| Concurrency | Implement transaction / optimistic locking | Nghia |  | 2026-10-15: 8
Web
| Web | Implement Manager leave / swap approval screens | Hien |  | 2026-10-15: 10
| Web | Implement Open Shift management screen | Hien |  | 2026-10-15: 7
React Native
| React Native | Implement Leave Request UI (React Native) | Quan |  | 2026-10-15: 7
| React Native | Implement Shift Swap / Open Shift Claim UI (React Native) | Quan |  | 2026-10-15: 10
Attendance
| Attendance | Implement GPS Check-in / Check-out UI (React Native) | Quan |  | 2026-10-15: 9
| Attendance | Implement server-time / geofence validation API | Tuan |  | 2026-10-15: 10
| Attendance | Implement Attendance event storage | Nghia |  | 2026-10-15: 7
AI Support
| AI Support | Implement candidate-filter fallback in Laravel | Tuan |  | 2026-10-15: 7
| AI Support | Implement optional AI replacement explanation | Luc |  | 2026-10-15: 8
Notification
| Notification | Implement leave / swap / Open Shift notifications | Luc |  | 2026-10-15: 6
Testing
| Testing | Concurrent Open Shift acceptance test | Nghia |  | 2026-10-15: 7
| Testing | GPS attendance boundary / accuracy tests | Quan |  | 2026-10-15: 6
| Testing | Leave / Swap / Open Shift E2E tests | Hien |  | 2026-10-15: 6
Release
| Release | Bug fixing & Sprint 3 release | Luc |  | 2026-10-15: 8
|  |  | TOTAL | 0 | 2026-10-15: 183

## Chart
Burn down chart Sprint 3
Estimate | Actual | Date
178 |  | 2026-10-15
172.5 |  | 2026-10-16
164.5 |  | 2026-10-17
155 |  | 2026-10-18
147 |  | 2026-10-19
137.5 |  | 2026-10-20
126 |  | 2026-10-21
117 |  | 2026-10-22
103 |  | 2026-10-23
91 |  | 2026-10-24
81.5 |  | 2026-10-25
72 |  | 2026-10-26
60.5 |  | 2026-10-27
51 |  | 2026-10-28
40.5 |  | 2026-10-29
26.5 |  | 2026-10-30
16.5 |  | 2026-10-31
8 |  | 2026-11-01
4 |  | 2026-11-02
2 |  | 2026-11-03
0 |  | 2026-11-04
0 |  | 2026-11-05