## Estimate
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 4 - Timesheet, Reporting, AI Assistant & System Hardening
Development Team: |  | C1SE.57
Start Date: |  | 2026-11-06
End Date: |  | 2026-11-27
On Time
No. | Member Name | Full Name | Estimate |  |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 40 |  |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 37 |  |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 41
4 | Quan | Huỳnh Văn Minh Quân | 37
5 | Luc | Huỳnh Vũ Lực | 31
Total |  |  | 186
SPRINT 4 REPORT | Component | Task Name | Responsible Member | Estimate | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27
Planning
| Planning | Sprint Planning Meeting | Tuan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planning | Create Sprint Backlog & Test Plan | Tuan | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design
| Design | Design Timesheet reconciliation & approval UI | Hien | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design Dashboard & Report UI | Hien | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | Design AI Assistant UI / service status | Quan | 5 | 5 | 5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database
| Database | Update Timesheet / audit / AI request schema | Nghia | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timesheet
| Timesheet | Implement attendance-to-timesheet calculation | Nghia | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Timesheet | Implement grace / break / rounding / overtime rules | Tuan | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Timesheet | Implement Manager correction / approval APIs | Tuan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Web
| Web | Implement Timesheet review / approval screen | Hien | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dashboard
| Dashboard | Implement staffing / attendance dashboard APIs | Nghia | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 4.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dashboard | Implement dashboard charts / filters | Hien | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 5.5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reporting
| Reporting | Implement PDF / Excel export | Tuan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting | Implement estimated labor-cost summary | Nghia | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AI
| AI | Build optional AI Service (FastAPI / LLM API) | Luc | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AI | Implement verified-data explanation endpoints | Luc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AI | Implement AI graceful degradation / timeout | Luc | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring
| Monitoring | Implement service health / job-status page | Quan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
React Native
| React Native | Implement Timesheet & notification views (React Native) | Quan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality
| Quality | Responsive React Web / React Native UI refinement | Quan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing
| Testing | End-to-End workflow test | Hien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | Security / RBAC regression tests | Tuan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | Graceful degradation tests for AI/Scheduling | Luc | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | Performance & data integrity tests | Nghia | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4.5 | 2.5 | 0 | 0 | 0 | 0 | 0
Release
| Release | System integration, bug fixing & Sprint 4 release | Quan | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 5 | 2.5 | 0 | 0
|  |  | TOTAL | 186 | 181 | 177.5 | 172 | 164.5 | 157 | 149 | 139 | 129.5 | 113.5 | 97.5 | 79.5 | 64 | 53.5 | 42.5 | 32 | 21.5 | 12.5 | 7.5 | 5 | 2.5 | 0 | 0

## Actual
Project Name: |  | Smart Scheduling - Website for Automated Staff Scheduling and Shift
Module Name: |  | Sprint 4 - Timesheet, Reporting, AI Assistant & System Hardening
Development Team: |  | C1SE.57
Start Date: |  | 2026-11-06
End Date: |  | 2026-11-27
On Time
No. | Member Name | Full Name | Estimate | Actual |  |  | Lately
1 | Tuan | Lê Hà Đức Tuấn | 40 | 0 |  |  | Early
2 | Hien | Lê Trần Thanh Hiền | 37 | 0 |  |  | Unfinished
3 | Nghia | Lê Đình Nghĩa | 41 | 0
4 | Quan | Huỳnh Văn Minh Quân | 37 | 0
5 | Luc | Huỳnh Vũ Lực | 31 | 0
Total |  |  | 186 | 0
SPRINT 4 REPORT | Component | Task Name | Responsible Member | Actual | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27
Planning
| Planning | Sprint Planning Meeting | Tuan |  | 2026-11-06: 3
| Planning | Create Sprint Backlog & Test Plan | Tuan |  | 2026-11-06: 4
Design
| Design | Design Timesheet reconciliation & approval UI | Hien |  | 2026-11-06: 5
| Design | Design Dashboard & Report UI | Hien |  | 2026-11-06: 6
| Design | Design AI Assistant UI / service status | Quan |  | 2026-11-06: 5
Database
| Database | Update Timesheet / audit / AI request schema | Nghia |  | 2026-11-06: 8
Timesheet
| Timesheet | Implement attendance-to-timesheet calculation | Nghia |  | 2026-11-06: 10
| Timesheet | Implement grace / break / rounding / overtime rules | Tuan |  | 2026-11-06: 10
| Timesheet | Implement Manager correction / approval APIs | Tuan |  | 2026-11-06: 8
Web
| Web | Implement Timesheet review / approval screen | Hien |  | 2026-11-06: 9
Dashboard
| Dashboard | Implement staffing / attendance dashboard APIs | Nghia |  | 2026-11-06: 9
| Dashboard | Implement dashboard charts / filters | Hien |  | 2026-11-06: 9
Reporting
| Reporting | Implement PDF / Excel export | Tuan |  | 2026-11-06: 8
| Reporting | Implement estimated labor-cost summary | Nghia |  | 2026-11-06: 7
AI
| AI | Build optional AI Service (FastAPI / LLM API) | Luc |  | 2026-11-06: 10
| AI | Implement verified-data explanation endpoints | Luc |  | 2026-11-06: 8
| AI | Implement AI graceful degradation / timeout | Luc |  | 2026-11-06: 6
Monitoring
| Monitoring | Implement service health / job-status page | Quan |  | 2026-11-06: 7
React Native
| React Native | Implement Timesheet & notification views (React Native) | Quan |  | 2026-11-06: 8
Quality
| Quality | Responsive React Web / React Native UI refinement | Quan |  | 2026-11-06: 7
Testing
| Testing | End-to-End workflow test | Hien |  | 2026-11-06: 8
| Testing | Security / RBAC regression tests | Tuan |  | 2026-11-06: 7
| Testing | Graceful degradation tests for AI/Scheduling | Luc |  | 2026-11-06: 7
| Testing | Performance & data integrity tests | Nghia |  | 2026-11-06: 7
Release
| Release | System integration, bug fixing & Sprint 4 release | Quan |  | 2026-11-06: 10
|  |  | TOTAL | 0 | 2026-11-06: 186

## Chart
Burn down chart Sprint 4
Estimate | Actual | Date
181 |  | 2026-11-06
177.5 |  | 2026-11-07
172 |  | 2026-11-08
164.5 |  | 2026-11-09
157 |  | 2026-11-10
149 |  | 2026-11-11
139 |  | 2026-11-12
129.5 |  | 2026-11-13
113.5 |  | 2026-11-14
97.5 |  | 2026-11-15
79.5 |  | 2026-11-16
64 |  | 2026-11-17
53.5 |  | 2026-11-18
42.5 |  | 2026-11-19
32 |  | 2026-11-20
21.5 |  | 2026-11-21
12.5 |  | 2026-11-22
7.5 |  | 2026-11-23
5 |  | 2026-11-24
2.5 |  | 2026-11-25
0 |  | 2026-11-26
0 |  | 2026-11-27